## Sheet1
Date | Schedule | Deliverable
2024-10-02 | Sprint 1 | Foundation Setup
2024-10-05 |  | Fundamental Features and Authentication
2024-10-07 |  | Creation of User Database ,setting up login
2024-10-23 | Sprint 2 | Control Manager
2024-10-23 |  | Purchase Order Management and Tracking
2024-10-28 |  | Develop Order Tracking System
2024-10-30 | Project Demo | Demonstration of Project Progress
2024-11-01 |  | Interface for Purchase Orders
2024-11-06 | Sprint 3 | Security
2024-11-08 |  | Selection of Authentication Techniques
2024-11-13 | Prototype Demo | Dicussion of our Project Prototype and the Document
2024-11-20 | Sprint 4 | Testing
2024-11-22 |  | Integration and Testing
2024-11-26 |  | Completion Of The Final Project
2024-12-04 | Final Project | Presentations based on feedback given in demo